## 1. Executive Summary
AyurMuni — Doctor & Vendor Dashboard Functionality Status
Document for Management ¦ Codebase review date: 2026-09-29 ¦ Scope: Frontend features currently implemented & API-wired
Purpose
This document summarizes, module by module, what is currently working in the Doctor Dashboard and Vendor Dashboard. Status is based on frontend code and API service wiring (not live UAT). Use it to brief management on what is done and what is still pending.
Overall Snapshot
Dashboard | Working Modules | Partial / Hidden | Coming Soon | Overall Readiness (Frontend) | Notes for Management
Doctor Dashboard | Login, Onboarding, Dashboard, Availability, Appointments (+ Details), Patients, Video Call, Messenger, Diets*, Do's & Don'ts*, Reviews, Profile | Earnings/Finance (built but hidden from menu), Help & Support (UI heavy / limited API), Notifications | — | High — core clinical workflow is in place | * Diets and Do's & Don'ts show only for dietitian doctors (is_dietitian flag). Unverified doctors see Verification Pending instead of full menu.
Vendor Dashboard | Login, Onboarding, Dashboard, Products (Add/Edit/Detail/Bulk), Stock, Banners, Catalog, Orders (+ Detail), Customers (via Orders), Ratings, Profile, Notifications | Settings (limited tabs), Order status actions (mock fallback), Help & Support (static FAQ) | Finance, Analytics, Coupons (Soon badge; Coming Soon page) | High for catalog & orders; Finance/Analytics/Coupons still gated | Forgot/Reset password pages exist but are not routed (OTP login only). Unverified vendors see Verification Pending instead of full menu.
Status Legend
Status | Meaning
Working | Feature is implemented in UI and calls live backend APIs.
Partially Working | Some features work; others incomplete, mocked, or limited.
Coming Soon | Route/menu exists but shows a Coming Soon / Unavailable page.
Hidden / Not in Menu | Feature code & route exist, but navigation item is commented/hidden.
UI Only (No Live API) | Screens exist mainly with static or mock data; not production-ready.
Not Available | Not exposed to users / not wired for use.
How to read the other sheets
Sheet 2 = Doctor modules detail ¦ Sheet 3 = Vendor modules detail ¦ Sheet 4 = Side-by-side comparison ¦ Sheet 5 = Gaps & next priorities for management

## 2. Doctor Dashboard
Doctor Dashboard — Module-wise Functionality
All modules listed from login to end-of-flow. Status reflects frontend implementation + API service calls found in code.
# | Module | Route(s) | Status | What Currently Works (User Features) | API Connected? | Gaps / Notes
1 | Login / Authentication | /login | Working | Shared login for Doctor & Vendor OTP-based mobile login Role selection when user has multiple roles Session token stored; protected routes | Yes — authService | Forgot/Reset password pages exist but are currently unrouted (OTP login only).
2 | Doctor Onboarding | /doctor/onboarding | Working | Multi-step onboarding profile Prakriti & health disease selection Document upload Bank details submission Redirects away if profile already completed | Yes — doctorService | Required before full access; verification gate applies after submit.
3 | Verification Gate | Sidebar (all modules) | Working | If profile.verify = false, full menu is hidden Shows Verification Pending card (12–24 hrs) Contact Support button | Yes — profile.verify from session | Doctor cannot use main modules until verified.
4 | Dashboard | /doctor/dashboard | Working | Overview KPIs / summary cards Follow-up patients data Quick view of practice activity | Yes — dashboardget, dashboardfolloupadata | —
5 | Availability (Calendar) | /doctor/availability | Working | Monthly calendar view Create time slots Update / delete slots Slot drawer & booking details UI Availability stats | Yes — availability CRUD APIs | —
6 | Appointments (List) | /doctor/appointments | Working | List appointments by type/status Pagination & filters Accept / reject / reschedule actions Delete appointment Open appointment detail | Yes — getAppointment, updateAppointmentstatus | —
7 | Appointment Details | /doctor/appointments/:type/:id | Working | Full consultation detail Write / edit prescription (medicine search) Upload / delete appointment documents Assign / replace diet plan View Do's & Don'ts by prakriti Patient questionnaire Diet progress tracking Start video call (floating window) | Yes — extensive doctorService endpoints | Core clinical workflow is the most complete doctor module.
8 | Patients | /doctor/patients | Working | Patient list with pagination Search, prakriti & gender filters Open patient appointment/detail flow | Yes — getPatient | Dedicated Patient Detail route is commented out; detail opens via Appointment Details path.
9 | Video Consultation | /doctor/videocall/:id + floating window | Working | Agora-based video call Draggable doctor video window Call status & token fetch Mute/camera controls, waiting screen Patient join via patvideocall route | Yes — appointmentCallService (Agora) | Patient video page supports patient-app integration.
10 | Messenger (Chat) | /doctor/messenger(/:patientId) | Working | Conversation list Search conversations Open chat by patient Send/receive consultation messages | Yes — consultationChatService | —
11 | Diets (Dietitian only) | /doctor/diets, add-diet, edit-diet, bulk-upload | Working | Diet plan list with search/filters Create / edit / delete diet plans Bulk Excel upload Visible only if is_dietitian = true | Yes — diet CRUD + bulkupload | Hidden for non-dietitian doctors.
12 | Do's & Don'ts (Dietitian only) | /doctor/do-donts, add, edit | Working | Template list & search Filter by prakriti / disease Create / edit templates Detail view | Yes — DoDonts template APIs | Shown in sidebar only for dietitians.
13 | Earnings / Finance | /doctor/earnings | Hidden / Not in Menu | Finance metrics dashboard UI exists Financial KPIs fetch | Yes — financedashboard API wired | Sidebar menu item is commented out. Route works if opened directly. Not exposed in navigation.
14 | Reviews & Feedback | /doctor/reviews | Working | Doctor review insights List reviews Reply / update / delete reply | Yes — reviewService | —
15 | Help & Support | /doctor/help-support | UI Only (No Live API) | FAQ / contact style UI Support tickets UI (local sample data) Create ticket form UI | Mostly UI — tickets appear local/static | Sidebar Help item commented out; reachable via Verification Pending Contact Support.
16 | Profile & Settings | /doctor/profile (settings → profile) | Working | View / edit profile Documents upload Bank details add/update Change password Delete account | Yes — profile, bank, documents, password APIs | Settings redirects to Profile.
17 | Notifications | /doctor/notifications | Partially Working | Notifications page routed for doctor Mark read / list patterns exist | Yes — notification endpoints | Not a primary sidebar item; access mainly via header.
18 | Policies (Public) | /privacy-policy, /terms-conditions | Working | Privacy Policy page Terms of Use page | Yes — public policy pages | No login required.

## 3. Vendor Dashboard
Vendor Dashboard — Module-wise Functionality
All modules listed from login to end-of-flow. Coming Soon items are intentionally gated in App.js with UnavailableFeature pages.
# | Module | Route(s) | Status | What Currently Works (User Features) | API Connected? | Gaps / Notes
1 | Login / Authentication | /login | Working | OTP-based login (shared with Doctor) Role selection Protected vendor routes Unauthorized page | Yes — authService | Forgot/Reset password components exist but routes are commented out.
2 | Vendor Onboarding | /vendor/onboarding | Working | Business/profile onboarding Document upload Redirect if already completed | Yes — createOnboarding, uploadfiles | Verification pending gate after submit.
3 | Verification Gate | Sidebar | Working | Unverified vendors see pending state instead of menu Contact Support shortcut | Yes — profile.verify | Same pattern as Doctor.
4 | Dashboard | /vendor/dashboard | Working | KPI cards (products, stock, orders, finance snippet) Recent products / orders / reviews Notifications snippets Charts widgets | Yes — products, inventory, orders, finance, reviews, notifications | Finance snippet soft-fails if finance API unavailable.
5 | Products / Inventory List | /vendor/products | Working | Product list with search Pagination Delete product Update variant status Navigate to detail / edit / add | Yes — getProducts, deleteProduct, updateVariants | —
6 | Add Product | /vendor/new-product | Working | Full product create form Variants + image upload Brand / subcategory / health diseases Tax / UniCommerce related fields | Yes — addProduct, uploadfiles, field info | —
7 | Edit Product | /vendor/edit-product/:id | Working | Load existing product Update product & variants Add/delete variants Image upload | Yes — getSingleProduct, updateProduct, variants APIs | —
8 | Product Detail | /vendor/products/:id | Working | View product & variant details Inventory snapshot for product | Yes — getSingleProduct, getInventory | —
9 | Bulk Upload Products | /vendor/bulk-upload-products | Working | Excel bulk upload of products Upload progress / result handling | Yes — bulkUploadProducts | —
10 | Stock Management | /vendor/stock | Working | Inventory list & search Filter by product Update stock quantities Delete inventory row | Yes — inventory CRUD APIs | —
11 | Banners | /vendor/banners | Working | List / create / edit / delete banners Image upload Link URL field | Yes — banner APIs + uploadfiles | —
12 | Catalog | /vendor/catalog | Working | Browse categories, subcategories, brands Search across catalog fields Taxonomy reference for products | Yes — getFieldInfo APIs | Read-oriented catalog browser.
13 | Orders | /vendor/orders | Working | Order list with search & filters Orders summary cards Open order detail Customers view toggle inside Orders | Yes — getOrders, getOrdersSummary | Order status update currently uses mock fallback / rejects if mocks off.
14 | Order Detail | /vendor/orders/:id | Working | Full order detail view Items, customer, payment/status info | Yes — getOrder | —
15 | Customers | /vendor/customers → Orders?view=customers /vendor/customers/:id | Partially Working | Customers panel inside Orders Customer list/search via API Customer detail page | Yes — customerService | Standalone /customers redirects into Orders customers view.
16 | Finance (Wallet / Settlements / Withdrawals) | /vendor/finance (+ subroutes) | Coming Soon | Shows Coming Soon / Unavailable page (Full Finance UI code exists but is not mounted) | APIs exist in vendorService but routes are gated | Sidebar shows Finance with Soon badge. Do not present as live.
17 | Analytics | /vendor/analytics | Coming Soon | Coming Soon page only (Analytics.jsx exists but not routed live) | Component can call APIs; App mounts UnavailableFeature | Sidebar Soon badge.
18 | Coupons | /vendor/coupons | Coming Soon | Coming Soon page in routes (Coupons.jsx exists; couponService defaults to mocks) | Mock by default (REACT_APP_USE_MOCKS) | Not production-ready; sidebar Soon.
19 | Ratings & Reviews | /vendor/ratings | Working | List reviews Search & filters Reply / update / delete reply Report review | Yes — reviewService vendor APIs | —
20 | Help & Support | /vendor/help-support | UI Only (No Live API) | Static contact cards (email/phone) FAQ accordion Guidance for verification & stock | No ticket API — informational only | Useful page; not a live support ticket system.
21 | Settings | /vendor/settings | Partially Working | Store settings tab Change password (auth API) Other tabs commented out | Yes for change-password | Limited scope vs full settings module.
22 | Profile | /vendor/profile | Working | View/edit vendor profile Document uploads Bank details CRUD Account management | Yes — profile + bank-details APIs | —
23 | Notifications | /vendor/notifications | Working | Notification list Mark read / mark all read Unread count on dashboard | Yes — notificationService | —

## 4. Side-by-Side Comparison
Doctor vs Vendor — Capability Comparison (for Management)
Capability Area | Doctor Dashboard | Vendor Dashboard | Management Takeaway
Authentication | Working (OTP) | Working (OTP); Forgot/Reset not routed | Login is ready for both roles.
Onboarding + Verification | Working | Working | Both require verification before full menu.
Home Dashboard | Working | Working | Both have live KPI dashboards.
Core Workflow | Appointments, Patients, Prescription, Video, Chat — Working | Products, Stock, Orders, Catalog, Banners — Working | Primary business flows are live on both sides.
Catalog / Content tools | Diets + Do's & Don'ts (dietitian) | Products + Bulk upload + Banners + Catalog | Content tools are role-specific and largely complete.
Messaging / Calls | Messenger + Agora Video — Working | N/A | Doctor telehealth stack is implemented.
Reviews | Working | Working | Both can view/reply to reviews.
Finance / Payouts | Built but Hidden from menu | Coming Soon (gated) | Finance is the largest shared gap for go-live messaging.
Analytics | N/A (embedded in dashboard) | Coming Soon | Vendor analytics not released yet.
Coupons / Promotions | N/A | Coming Soon (mock-backed) | Do not market coupons as live.
Help & Support | UI-heavy / limited backend | Static FAQ + contacts | Support is informational; no full ticket backend yet.
Profile / Settings | Working | Profile Working; Settings partial | Account management is usable.

## 5. Gaps & Priorities
What Is Done vs What Remains — Recommended Priorities
A. Already Done (safe to present as Working)
# | Dashboard | Module | Business Value | Ready to Demo?
1 | Doctor | Appointments + Details (Rx, docs, diet assign) | Core consultation delivery | Yes
2 | Doctor | Availability calendar | Slot management for bookings | Yes
3 | Doctor | Video call + Messenger | Telehealth delivery | Yes
4 | Doctor | Diets & Do's & Don'ts (dietitian) | Dietitian care plans | Yes
5 | Doctor | Reviews + Profile + Onboarding | Trust & account setup | Yes
6 | Vendor | Products (Add/Edit/Bulk/Detail) | Catalog selling readiness | Yes
7 | Vendor | Stock Management | Inventory accuracy | Yes
8 | Vendor | Orders + Order Detail + Customers panel | Order operations | Yes
9 | Vendor | Banners + Catalog + Ratings | Storefront & reputation | Yes
10 | Both | Login + Onboarding + Verification gate | Secure access control | Yes
B. Gaps / Not Ready (do not present as fully live)
# | Dashboard | Item | Current State | Suggested Action
1 | Vendor | Finance (wallet/settlements/withdrawals) | Coming Soon page; UI code exists offline | Enable after payout APIs UAT; then remove Soon badge.
2 | Vendor | Analytics | Coming Soon page | Wire Analytics.jsx when metrics stable.
3 | Vendor | Coupons | Coming Soon + mock service default | Switch off mocks only when coupon APIs ready.
4 | Doctor | Earnings / Finance | API wired but menu hidden | Product decision: unhide after finance UAT.
5 | Both | Help & Support ticketing | Mostly static / UI sample | Integrate real ticket APIs if needed for ops.
6 | Vendor | Forgot / Reset password | Pages exist, routes commented | Keep OTP-only or re-enable routes deliberately.
7 | Vendor | Order status actions | Mock fallback in orderService | Connect real status-update API before ops use.
8 | Doctor | Dedicated Patient Detail page | Route commented; uses Appointment Details | OK if intentional; else restore dedicated page.
C. One-line message for Management
Doctor Dashboard: Clinical workflow (availability → appointments → prescription/diet → video/chat → reviews) is largely complete; earnings menu is held back. Vendor Dashboard: Catalog, stock, orders, banners, and ratings are largely complete; Finance, Analytics, and Coupons are intentionally Coming Soon.
Document note: Status is from frontend codebase review (routes, UI modules, and service API calls). Live backend UAT may find additional API readiness issues.