## Cover
AYURMUNI
Doctor & Vendor Dashboard — Functionality Tracker
Document Type: Management Functionality Status Report
Review Date: 29 September 2026
Prepared for: Management / Product Leadership
Scope: Frontend modules currently implemented, with working logic and blockers
HOW TO READ THIS DOCUMENT
1. Open sheet: Doctor Functionality OR Vendor Functionality 2. Each MODULE name appears as a green centered bold banner 3. Under every module, each FEATURE is listed with: • Feature name • Working logic (how the feature works for the user) • Status (dropdown — Working / Partially Working / Coming Soon / Not Working / UI Only / Hidden) • Blocker / Gap (what is stopping full completion, if any) 4. You can change Status using the dropdown in the Status column. 5. Sheet Summary shows counts by status for quick reporting.
STATUS MEANING
Status | Meaning
Working | Feature is live in UI and connected to backend API.
Partially Working | Main flow works, but some part is incomplete / mock / limited.
Coming Soon | Shown in menu/route as Coming Soon — not released to users.
Not Working | Feature appears but does not complete the intended action.
UI Only | Screen/UI exists but no live backend integration.
Hidden | Code/route exists but is hidden from the user menu.
SHEETS IN THIS WORKBOOK
• Cover — How to read + status legend • Doctor Functionality — All doctor modules & features • Vendor Functionality — All vendor modules & features • Summary — Counts for management reporting

## Summary
Management Summary — Status Counts
How counts are calculated
Counts below are based on Feature rows in Doctor Functionality and Vendor Functionality sheets.
Doctor Dashboard
Status | Feature Count
Working | 59
Partially Working | 2
Coming Soon | 0
Not Working | 2
UI Only | 4
Hidden | 5
TOTAL FEATURES | 72
Vendor Dashboard
Status | Feature Count
Working | 39
Partially Working | 2
Coming Soon | 6
Not Working | 4
UI Only | 1
Hidden | 4
TOTAL FEATURES | 56
Management Message
Doctor Dashboard: Clinical workflow is largely complete (Availability → Appointments → Prescription/Diet → Video/Chat → Reviews). Earnings is hidden from menu and payout is not live. Help & Support is UI-only. Vendor Dashboard: Catalog operations are largely complete (Products, Stock, Banners, Catalog, Order viewing, Ratings). Finance, Analytics, and Coupons are Coming Soon. Order status actions and Product Duplicate are not working yet.

## Doctor Functionality
Doctor Dashboard — Module & Feature Functionality Tracker
Professional functionality tracker for management ¦ Updated: 2026-09-29 ¦ Status column has dropdown ¦ Green banner = Module start
Module | Feature | Feature Working Logic (How it works) | Status | Blocker / Gap
MODULE 1: Login & Authentication
Login & Authentication | OTP Login | User enters mobile number → system sends OTP → user verifies OTP → session token is stored → user is redirected to Doctor Dashboard or Onboarding based on profile completion. | Working | None
Login & Authentication | Role Selection | If the same mobile number has both Doctor and Vendor roles, user selects which dashboard to open after OTP verification. | Working | None
Login & Authentication | Register New Account | New user can register via OTP flow and create doctor/vendor account, then continue to onboarding. | Working | None
Login & Authentication | Account Restore | Deleted/inactive account can be restored through restore-account API during login flow. | Working | None
Login & Authentication | Forgot / Reset Password | Password reset pages exist in code but are not linked in routing because product currently uses OTP-only login. | Hidden | Routes are commented out in App.js. Product decision needed to re-enable.
MODULE 2: Doctor Onboarding
Doctor Onboarding | Multi-step Profile Setup | Doctor completes a guided wizard: Personal → Contact → Professional → Documents → Bank → Agreement. Each step validates required fields before next. | Working | None
Doctor Onboarding | Document Upload | Doctor uploads required professional documents during onboarding; files are sent to backend via document/upload APIs. | Working | None
Doctor Onboarding | Bank Details Capture | Doctor submits bank/UPI details in onboarding for future payouts/settlements. | Working | None
Doctor Onboarding | Legal Policy Acceptance | Doctor must review and accept required legal policies before final onboarding submit. | Working | None
Doctor Onboarding | Auto Redirect if Already Completed | If profile email already exists, system redirects doctor away from onboarding to dashboard. | Working | None
MODULE 3: Verification Gate
Verification Gate | Pending Verification Screen | If profile.verify is false, sidebar menu is hidden and doctor sees Verification Pending message with estimated 12–24 hour approval time. | Working | None
Verification Gate | Contact Support from Pending State | From pending screen, doctor can open Help & Support to contact team while waiting for verification. | Working | Help & Support itself is mostly UI-only (see Help module).
MODULE 4: Dashboard
Dashboard | Practice Summary KPIs | Dashboard loads doctor metrics (patients, consultations, appointments, revenue) from dashboard API and shows summary cards. | Working | None
Dashboard | Today / Upcoming Appointments | Shows today's appointments and upcoming consultations with navigation to appointment modules. | Working | None
Dashboard | Follow-up Patients Widget | Loads follow-up patient list from dedicated follow-up API and displays on dashboard. | Working | None
Dashboard | In-dashboard Chat Preview | UI shows a chat/messages area on dashboard for quick look. | UI Only | Chat messages on dashboard are hardcoded sample data, not live messenger API.
Dashboard | Trend Percentage on KPI Cards | Cards show growth percentages (e.g. +12%). | UI Only | Trend % values are hardcoded in UI, not calculated from API.
MODULE 5: Availability (Calendar)
Availability (Calendar) | Monthly Calendar View | Doctor opens Availability page → system fetches monthly slots from API → calendar shows available/booked days. | Working | None
Availability (Calendar) | Create Time Slot | Doctor selects day/time → fills slot drawer → submits → API creates availability slot → calendar refreshes. | Working | None
Availability (Calendar) | Update Time Slot | Doctor edits an existing slot → changes time/capacity/settings → API updates slot. | Working | None
Availability (Calendar) | Delete Time Slot | Doctor deletes a slot from drawer/card → API removes slot → calendar updates. | Working | None
Availability (Calendar) | Booking Details Modal | Doctor can open booked slot details to view booking information for that availability. | Working | None
Availability (Calendar) | Service Fee / Duration Config | Availability uses doctor service configuration (fee/duration) from policy/config API. | Working | None
MODULE 6: Appointments
Appointments | Appointment List | Doctor opens Appointments → API returns paginated list → doctor can search and filter by status/date. | Working | None
Appointments | Accept / Reject / Reschedule | Doctor takes action on appointment (with timing rules, e.g. reschedule rules) → status update API is called → list refreshes. | Working | None
Appointments | Open Appointment Detail | Clicking an appointment opens full consultation detail page for clinical actions. | Working | None
Appointments | Assessments Menu Shortcut | Assessments route exists but only redirects doctor to Appointments list. | Hidden | No separate Assessments module; redirect only.
MODULE 7: Appointment Details (Consultation)
Appointment Details (Consultation) | Consultation Overview | Loads full appointment/patient context from detail API and shows clinical tabs. | Working | None
Appointment Details (Consultation) | Write / Edit Prescription | Doctor searches medicines → adds prescription items → create/edit prescription via API → can print template. | Working | None
Appointment Details (Consultation) | Upload / Manage Documents | Doctor uploads appointment documents → files stored via API → can view/delete documents. | Working | None
Appointment Details (Consultation) | Assign / Replace Diet Plan | Doctor searches diet plans → assigns or replaces diet plan for patient through diet plan APIs. | Working | None
Appointment Details (Consultation) | Patient Questionnaire | Doctor views patient onboarding questions and can fill/submit answers via patient-onboarding APIs. | Working | None
Appointment Details (Consultation) | Diet Progress Tracking | Doctor views prescribed diet plan progress day-wise for the patient. | Working | None
Appointment Details (Consultation) | View Do's & Don'ts by Prakriti | System loads Do's & Don'ts guidance based on patient prakriti for consultation support. | Working | None
Appointment Details (Consultation) | Start Video Call | Doctor clicks Join Call → floating Agora video window opens and connects using call token/status APIs. | Working | None
MODULE 8: Patients
Patients | Patient List | Doctor opens Patients → API returns paginated patients → supports search and prakriti/gender filters. | Working | None
Patients | Open Patient Clinical View | Selecting a patient opens consultation detail flow (type=patient) for clinical history/actions. | Working | None
Patients | Dedicated Patient Detail Page | A separate Patient Detail page was planned in routing. | Hidden | Route/import is commented out. Current flow uses Appointment Details instead.
MODULE 9: Video Consultation
Video Consultation | Doctor Agora Video Call | Doctor joins consultation → system fetches Agora token + call status → video/audio session starts with controls (mute, camera, hangup). | Working | None
Video Consultation | Floating Call Window | Call can open as a draggable floating window over dashboard pages so doctor can multitask. | Working | None
Video Consultation | Patient Join Reference Page | Public patient video join route exists for patient-app integration reference. | Working | Patient app integration is outside this repository.
MODULE 10: Messenger (Chat)
Messenger (Chat) | Conversation List | Doctor opens Messenger → conversations are fetched → searchable list of patients/chats is shown. | Working | None
Messenger (Chat) | Open Patient Thread | Selecting a conversation loads message history for that patient and opens chat pane. | Working | None
Messenger (Chat) | Send / Receive Messages | Messages are sent/received through consultation chat service (REST + WebSocket), with unread and access checks. | Working | None
Messenger (Chat) | Image Attachment in Chat | Doctor can upload/send image in conversation through upload + chat APIs. | Working | None
Messenger (Chat) | Online Presence Indicator | UI has online status concept for conversations. | Partially Working | Online status is currently forced to false in mapper.
MODULE 11: Diets (Dietitian Only)
Diets (Dietitian Only) | Diet Plan List | Dietitian opens Diets → searchable/filterable diet plan list loads from API. | Working | Visible only when profile.is_dietitian = true.
Diets (Dietitian Only) | Create Diet Plan | Dietitian fills plan details (meals/rules) → submits → API creates diet plan. | Working | None
Diets (Dietitian Only) | Edit Diet Plan | Dietitian opens existing plan → updates content → API saves changes. | Working | None
Diets (Dietitian Only) | Delete / Activate Diet Plan | Dietitian can delete plan or toggle plan active status via update/delete APIs. | Working | None
Diets (Dietitian Only) | Bulk Excel Upload | Dietitian uploads Excel file of diet plans → bulk upload API processes file and returns result. | Working | None
MODULE 12: Do's & Don'ts (Dietitian Nav)
Do's & Don'ts (Dietitian Nav) | Template List | List of Do's & Don'ts templates with search and prakriti/disease filters from API. | Working | Sidebar shows only for dietitians.
Do's & Don'ts (Dietitian Nav) | Create Template | Dietitian creates new Do's & Don'ts template and saves via create API. | Working | None
Do's & Don'ts (Dietitian Nav) | Edit Template | Dietitian opens template → updates content → update API saves changes. | Working | None
Do's & Don'ts (Dietitian Nav) | Delete Template | Ability to remove a template from list. | Not Working | No delete API/UI implemented.
MODULE 13: Earnings / Finance
Earnings / Finance | Earnings Dashboard (Read) | Page can load financial metrics and transactions from financedashboard API and show charts/stats. | Hidden | Sidebar Earnings menu item is commented out — not exposed to doctors.
Earnings / Finance | Transaction List / Search | Doctor can search/view financial transactions on earnings page UI. | Hidden | Same as above — feature exists but menu is hidden.
Earnings / Finance | Request Payout / Withdrawal | Payout request modal UI exists on earnings page. | Not Working | Submit does not call a payout API. Bank options are hardcoded. Blocker: payout API + product decision to unhide menu.
MODULE 14: Reviews & Feedback
Reviews & Feedback | Review List & Filters | Doctor opens Reviews → API returns reviews with search/filter/sort options and summary stats. | Working | None
Reviews & Feedback | Reply to Review | Doctor writes reply → reply API saves response on the review. | Working | None
Reviews & Feedback | Edit / Delete Reply | Doctor can update or delete an existing reply through review reply APIs. | Working | None
MODULE 15: Help & Support
Help & Support | FAQ / Contact UI | Help page shows FAQ and contact-style support channels. | UI Only | Mostly static UI. Sidebar Help item is commented out.
Help & Support | Support Ticket System | UI shows ticket list and create-ticket form. | UI Only | Tickets are local/sample data. No live ticket create/list API.
MODULE 16: Profile & Settings
Profile & Settings | View / Edit Profile | Doctor opens Profile → loads full profile → edits fields → update profile API saves changes. | Working | None
Profile & Settings | Document Management | Doctor can upload/update professional documents from Profile Documents tab. | Working | None
Profile & Settings | Bank Details Management | Doctor can add/update bank details from Profile Bank tab. | Working | None
Profile & Settings | Change Password | Doctor submits current + new password → auth change-password API updates credentials. | Working | None
Profile & Settings | Delete Account | Doctor can request account deletion via delete profile API. | Working | None
MODULE 17: Notifications
Notifications | Notification List | Doctor opens Notifications → list loads from notification API with tabs/load-more. | Working | None
Notifications | Mark Read / Mark All Read | Doctor marks one or all notifications read → API updates read state → unread badge refreshes. | Working | None
Notifications | Delete / Clear Notifications | Doctor can delete single notification or clear all via notification APIs. | Working | None
Notifications | Deep Link to Appointment | Clicking some notifications can navigate to related appointment detail. | Partially Working | Some click handlers still branch on vendor/order concepts.

## Vendor Functionality
Vendor Dashboard — Module & Feature Functionality Tracker
Professional functionality tracker for management ¦ Updated: 2026-09-29 ¦ Status column has dropdown ¦ Green banner = Module start
Module | Feature | Feature Working Logic (How it works) | Status | Blocker / Gap
MODULE 1: Login & Authentication
Login & Authentication | OTP Login / Register | Vendor enters mobile → OTP verify → token stored → redirect to Vendor Dashboard or Onboarding. | Working | None
Login & Authentication | Role Selection | If user has multiple roles, vendor/doctor choice is shown after OTP. | Working | None
Login & Authentication | Forgot / Reset Password | Forgot/Reset password screens exist in codebase. | Hidden | Routes commented in App.js. System is OTP-login only currently.
MODULE 2: Vendor Onboarding
Vendor Onboarding | Business Onboarding Wizard | Vendor completes Business → Contact → Bank → Documents → Agreement steps and submits profile. | Working | None
Vendor Onboarding | Document Upload | Vendor uploads KYC/business documents during onboarding via upload API. | Working | None
Vendor Onboarding | Legal Policy Acceptance | Vendor accepts required policies before completing onboarding. | Working | None
MODULE 3: Verification Gate
Verification Gate | Pending Verification Lock | If vendor is not verified, full sidebar menu is hidden and pending state is shown. | Working | None
Verification Gate | Limited Access while Pending | Unverified vendor can still reach support/profile-related paths as configured by protected route logic. | Working | None
MODULE 4: Dashboard
Dashboard | KPI Overview | Dashboard loads products, inventory, orders, notifications, reviews and shows KPI cards/charts. | Working | None
Dashboard | Recent Orders / Products / Reviews | Right panel and tables show recent business activity with deep links to modules. | Working | Orders/reviews/finance widgets soft-fail if those APIs fail.
Dashboard | Revenue KPI Link | Revenue card can navigate toward Finance. | Partially Working | Finance route is Coming Soon, so revenue deep-link lands on unavailable page.
MODULE 5: Products / Inventory
Products / Inventory | Product List | Vendor opens Products → paginated product list loads → can expand variants, view status, open detail/edit. | Working | Search currently filters only loaded page results (not full server-side search).
Products / Inventory | Add Product | Vendor fills product + multi-variant form (images, price, SKU, stock, brand, subcategory, etc.) → addProduct API creates product. | Working | None
Products / Inventory | Edit Product | Vendor opens edit page → product loads → updates product/variants → patch APIs save changes. | Working | None
Products / Inventory | Product Detail View | Vendor opens product detail → sees gallery, variants, pricing/stock, approval and inventory snapshot. | Working | None
Products / Inventory | Delete Product / Variant | Vendor deletes product or variant from list/edit flows via delete APIs. | Working | None
Products / Inventory | Toggle Variant Active Status | Vendor can activate/deactivate a variant from product list; status update API is called. | Working | None
Products / Inventory | Bulk Excel Upload | Vendor uploads Excel product file → bulk-upload API processes and returns created/skipped/errors. | Working | None
Products / Inventory | Duplicate Product | Detail page has Duplicate CTA intending to prefill Add Product from existing product. | Not Working | Add Product does not read ?duplicate=id query. Blocker: wire duplicate load logic.
MODULE 6: Stock Management
Stock Management | Inventory List & Filters | Vendor opens Stock → inventory rows load → can search/filter low/out/in-stock items. | Working | None
Stock Management | Update Stock Quantity | Vendor edits quantity on a row → update inventory API saves new stock value. | Working | None
Stock Management | Delete Inventory Row | Vendor deletes an inventory record via delete inventory API. | Working | None
Stock Management | Create Inventory Independently | Dedicated create-inventory form from Stock page. | Not Working | No create UI; stock is usually set during product add/edit.
MODULE 7: Banners
Banners | Banner List | Vendor opens Banners → existing banners load as cards/list. | Working | None
Banners | Create / Edit Banner | Vendor uploads banner image, sets redirect URL and active flag → create/update banner API saves. | Working | None
Banners | Delete Banner | Vendor deletes banner → delete API removes it from list. | Working | None
MODULE 8: Catalog
Catalog | Browse Categories / Subcategories / Brands | Vendor opens Catalog → taxonomy and products are loaded for reference browsing and search. | Working | Read-only reference browser (not taxonomy CRUD).
Catalog | Standalone Categories Page | Separate Categories management page file exists. | Hidden | No route mounted in App.js.
Catalog | Standalone Brands Page | Separate Brands management page file exists. | Hidden | No route mounted in App.js.
MODULE 9: Orders
Orders | Order List & Filters | Vendor opens Orders → order list + summary KPIs load → filter by status/payment/date/search. | Working | None
Orders | Order Detail View | Vendor opens an order → full detail shows items, payment, shipping, tracking, sync status. | Working | None
Orders | Order Status Actions (Accept / Pack / Ship) | Vendor should be able to update fulfillment status from dashboard. | Not Working | No status action buttons in UI. orderService.updateStatus is mock/unused. Blocker: real status-update API + UI actions.
Orders | Customers Tab inside Orders | Orders page has Customers view toggle listing customers with search/pagination. | Working | None
MODULE 10: Customers
Customers | Customer List | Customers are listed via customer API inside Orders customers view (or redirected path). | Working | Standalone /vendor/customers redirects into Orders view.
Customers | Customer Detail | Vendor opens customer detail → profile, addresses, order history load from customer get API. | Working | None
Customers | Edit Customer Notes / CRM Actions | CRM-style editable notes and customer actions. | Not Working | Notes are read-only if present. No CRM edit workflow.
MODULE 11: Finance
Finance | Finance Overview | Menu item exists for Finance earnings/settlements/payouts. | Coming Soon | App mounts Coming Soon page. Full Finance UI code exists but is not mounted. Blocker: payout/finance API UAT + enable routes.
Finance | Wallet Transactions | Wallet page intended to show wallet ledger. | Coming Soon | Route gated to Coming Soon. Orphan Wallet page exists.
Finance | Settlements | Settlements page intended for settlement history. | Coming Soon | Route gated. Orphan Settlements page used mock data.
Finance | Withdrawals | Withdrawal request form intended for payouts. | Coming Soon | Route gated. Orphan page was UI placeholder only.
MODULE 12: Analytics
Analytics | Sales / Performance Analytics | Analytics menu exists for charts and reports. | Coming Soon | Coming Soon page is mounted. Analytics.jsx exists but not live. Blocker: enable after metrics UAT.
MODULE 13: Coupons
Coupons | Coupon Management | Coupons menu exists for discount code create/list/delete. | Coming Soon | Coming Soon page mounted. Orphan Coupons UI uses mock service by default. Blocker: live coupon APIs + disable mocks.
MODULE 14: Ratings & Reviews
Ratings & Reviews | Review List & Filters | Vendor opens Ratings → reviews load with search/filters/stats. | Working | None
Ratings & Reviews | Reply to Review | Vendor replies to a review → reply API saves response. | Working | None
Ratings & Reviews | Edit / Delete Reply | Vendor can update or delete existing reply. | Working | None
Ratings & Reviews | Report Review | Vendor can report a review with reason/notes via report API. | Working | None
MODULE 15: Help & Support
Help & Support | Contact & FAQ Page | Shows email/phone/desk contacts and FAQ accordion for common vendor questions. | UI Only | No ticket/chat backend. FAQ text may be outdated vs live Orders.
MODULE 16: Settings
Settings | Store Settings Entry | Settings page opens but mainly guides/redirects vendor to Profile for store edits. | Partially Working | Business/Notifications/Security tabs are commented out. Limited settings surface.
Settings | Change Password from Settings | Password change form exists in code. | Hidden | Security tab not active in UI. OTP login is primary auth method.
MODULE 17: Profile
Profile | View / Edit Business Profile | Vendor opens Profile → loads profile → edits business/contact fields → update API saves. | Working | None
Profile | Document / Logo Upload | Vendor uploads documents or company logo via upload API from Profile. | Working | None
Profile | Bank Details CRUD | Vendor can add/update/select/delete bank details from Profile bank section. | Working | None
Profile | Delete Account | Vendor can delete account via delete profile API. | Working | None
MODULE 18: Notifications
Notifications | Notification Center | Vendor opens Notifications → list loads by tabs (all/order/inventory/system) with load-more. | Working | None
Notifications | Mark Read / Mark All Read | Vendor marks notifications read → API updates → header unread badge refreshes. | Working | None
Notifications | Deep Link by Notification Type | Opening a notification can navigate to related product/order/system destination. | Working | None